## 表紙
株式会社 トヨタコミュニケーションシステム 様
第1.00版
2017-07-21
グリーンシステム株式会社
ユーザー情報ＤＢ構築
データ取込ツール
結合・システム試験
仕様書

## CSV取込
結合・システム試験仕様書 |  |  |  | 機能名 | CSV取込(base_de_datos_importar.vbs) | 作成日 | 2017-07-13 |  | 検証日 | 2017-07-14 |  | 承認日 | 2017-07-14 |  | 正常
[6 empty] | 作成者 | 田中 |  | 検証者 | 畑 |  | 承認者 | 畑 |  | 異常
No | テスト分類 | 正常/異常 | 前提条件 | テスト手順 | 想定結果 | 1回目 |  |  | 2回目 |  |  | 確認
[6 empty] | 実施者 | 実施日 | 結果 | 実施者 | 実施日 | 結果 | 確認者 | 確認日 | 確認
1 | LOG出力先フォルダ作成 | 正常 | ログファイル格納先が存在しない | ログファイル格納先が存在しない状態で、DBサーバ上でスクリプトを実行する | ログファイル格納先が作成され、処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
2 |  | 正常 | ログファイル格納先が存在する | ログファイル格納先をあらかじめ作成後、DBサーバ上でスクリプトを実行する | 処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
3 | CSVファイル存在確認 | 正常 | 9種類の取込用CSVファイルが所定の場所に存在する | 取込用CSVファイルを所定の場所（初期設定ファイルのcsv_file_path）に配置し、DBサーバ上でスクリプトを実行する | 「存在確認=OK」がログに出力され、処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
4 | CSVファイル更新日確認 | 正常 | 9種類の取込用CSVファイルの1行目に書かれている日付が当日と等しい | すべてのCSVファイルの1行目に試験実施日当日が書かれている状態で、DBサーバ上でスクリプトを実行する | 本日日付と更新日と「OK」がログに出力され、処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
5 | CSVデータ整合性チェック（項目桁数確認）（チェック方法EXACT（データバイト数が等しいならOK）） | 正常 | 9種類の取込用CSVファイルの2行目から指定行数分（初期設定ファイルのcsv_check_row_num）の各項目の桁数が等しい | すべてのCSVファイルの2行目から指定行数分の各項目の桁数と初期設定ファイルで指定している桁数が等しい状態で、DBサーバ上でスクリプトを実行する | 処理が継続する CSVファイルデータ整合性確認内容：初期設定ファイルのcsv_check_format | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
6 | CSVデータ整合性チェック（項目桁数確認）（チェック方法LESS（データバイト数がこの桁数以下ならOK）） | 正常 | 9種類の取込用CSVファイルの2行目から指定行数分の各項目の桁数が指定桁数以下 | すべてのCSVファイルの2行目から指定行数分の各項目の桁数が初期設定ファイルで指定している桁数以下の状態で、DBサーバ上でスクリプトを実行する | 処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
7 | CSVデータ整合性チェック（項目数確認） | 正常 | 9種類の取込用CSVファイルの2行目から最終行までの各行の項目数が指定数と等しい | すべてのCSVファイルの2行目から最終行までの各行の項目数が初期設定ファイルで指定している項目数と等しい状態で、DBサーバ上でスクリプトを実行する | 処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
8 | ワークテーブル作成 | 正常 | 指定リトライ回数以内でDB接続正常 | DB接続が正常な状態で、DBサーバ上でスクリプトを実行する | DDL（テーブルクリエイト・リネーム・削除用）発行スクリプトファイル（初期設定ファイルのexec_ddl_filename及び引数"crear_tabla_temporal.sql"）が実行され、9個のワークテーブルが作成される | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
9 | DB取込 | 正常 |  |  | CSVインポート用スクリプトファイル（初期設定ファイルのimport_script_filename及びSQL Server Integration Services ( SSIS )パッケージファイル（SSIS_JINJI.bat）"SSISPKG"）が実行され、9個のワークテーブルにデータがインポートされる | 田中 | 2017-07-18 | NG | 田中 | 2017-07-18 | OK | 畑 | 2017-07-18 | OK
10 | ワークテーブル内データ数チェック | 正常 | 9個のワークテーブル内データ数、ヘッダー記載件数、CSVファイル行数がそれぞれ等しい | すべてのCSVファイルのヘッダー記載件数、データ行数、ワークテーブル内データ件数が等しく、DBサーバ上でスクリプトを実行する | 処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
11 | テーブルリネーム・削除 | 正常 | 指定リトライ回数以内でDB接続正常 | DB接続が正常な状態で、DBサーバ上でスクリプトを実行する | DDL（テーブルクリエイト・リネーム・削除用）発行スクリプトファイル（初期設定ファイルのexec_ddl_filename及び引数"reb_bor_tabla.sql"）が実行され、9個の予備テーブルが削除され、9個の運用（号口）テーブル名の先頭に「BK_」が付き、ワークテーブル名の先頭の「WK_」が削除される | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
12 | 取込済みCSVファイルバックアップ | 正常 | バックアップ先フォルダが存在しない | バックアップ先フォルダが存在しない状態で、DBサーバ上でスクリプトを実行する | バックアップ先フォルダが作成され、処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
13 |  | 正常 | バックアップ先フォルダが存在する | バックアップ先フォルダをあらかじめ作成後、DBサーバ上でスクリプトを実行する | バックアップ先フォルダにCSVファイルがコピーされ、処理が継続する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
14 |  | 正常 | バックアップフォルダに更新日が8日前以前のCSVファイルがある | バックアップフォルダに更新日が8日前以前のCSVファイルがある状態で、DBサーバ上でスクリプトを実行する | バックアップフォルダ内の、8日以前のファイルが削除される | 田中 | 2017-07-26 | OK |  |  |  | 畑 | 2017-07-26 | OK
15 |  | 正常 | バックアップフォルダに更新日が8日前以前のCSVファイル以外のファイルがある | バックアップフォルダに更新日が8日前以前の拡張子がCSVではないファイルがある状態で、DBサーバ上でスクリプトを実行する | バックアップフォルダ内の、8日以前のファイルが拡張子に関係なく削除される | 田中 | 2017-07-25 | OK |  |  |  | 畑 | 2017-07-25 | OK
16 |  | 正常 | バックアップフォルダに更新日が9日前以前のCSVファイルがある | バックアップフォルダに更新日が9日前以前のCSVファイルがある状態で、DBサーバ上でスクリプトを実行する | バックアップフォルダ内の、8日以前のファイルが削除されるので、9日前の日付ファイルも削除される | 田中 | 2017-07-25 | OK |  |  |  | 畑 | 2017-07-25 | OK
17 |  | 正常 | 当日受信したCSVファイルがあり、バックアップフォルダに当日コピーを実施している（当日2回目以降実行） | バックアップフォルダに当日コピー実施したCSVファイルがある状態で、DBサーバ上でスクリプトを実行する | バックアップフォルダ内の当日コピー実施済みのCSVファイルが上書きコピーされ、処理が継続する | 田中 | 2017-07-25 | OK |  |  |  | 畑 | 2017-07-25 | OK
18 | ログ出力 | 正常 | 初期設定ファイルのログレベル"INFO" | 初期設定ファイルのloglevelを"INFO"にした状態で、DBサーバ上でスクリプトを実行する | ログに[INFO]、[ERROR]が含まれた行が出力される | 田中 | 2017-07-25 | OK |  |  |  | 畑 | 2017-07-25 | OK
19 |  |  | 初期設定ファイルのログレベル"TRACE" | 初期設定ファイルのloglevelを"TRACE"にした状態で、DBサーバ上でスクリプトを実行する | ログに[INFO]、[ERROR]、[TRACE]が含まれた行が出力される | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
20 | インポート失敗時号口テーブル復旧コマンド | 正常 | 運用（号口）テーブルが9個揃っている | DBサーバでコマンドプロンプトを起動し、"exec_ddl.bat"が格納されているディレクトリへ移動し、コマンド（exec_ddl.bat recovery_goguchi.sql）を実行する | 運用（号口）テーブルがすべて削除され、先頭に「BK_」のついた予備テーブルがリネームされ運用（号口）テーブルになる | 田中 | 2017-07-25 | NG | 田中 | 2017-07-26 | OK | 畑 | 2017-07-26 | OK
21 |  |  | 運用（号口）テーブルが9個揃っていない |  |  | 田中 | 2017-07-25 | NG | 田中 | 2017-07-26 | OK | 畑 | 2017-07-26 | OK
22 | Windowsタスクスケジューラ登録して実行 | 正常 | 手動実行でエラーなく実行できるとき | CSV取込スクリプト(base_de_datos_importar.vbs)をWindowsタスクスケジューラに登録して、実行する ※ タスクの実行時に使うアカウントがCSVファイル格納先のアクセス権、バッチファイルの実行権限があること | タスクスケジューラの「前回の実行結果」に「この操作を正しく終了しました。（0x0）」と表示される | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
23 |  | 異常 | 手動実行でエラーが発生するとき |  | タスクスケジューラの「前回の実行結果」に「（0x[エラーCD]）」と表示される | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
24 |  |  |  |  | 初期設定ファイルで指定しているログ出力フォルダがログに出力され、処理が終了する | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
25 |  |  |  |  | 初期設定ファイルに記載された宛先（to_address、cc_address）とスクリプト内に記載された宛先（default_address）にエラー通知メールが送信される | 田中 | 2017-07-18 | OK |  |  |  | 畑 | 2017-07-18 | OK
26
27
28
29
30
31
32
33

## No20,21エビデンス
No.20
①復旧コマンド実行前
テーブル一覧 - 取得SQL：select * from sys.objects where type = 'U';
| name | object_id | principal_id | schema_id | parent_object_id | type | type_desc | create_date | modify_date | is_ms_shipped | is_published | is_schema_published
| BK_PERSON_OF_COMPANY | 1009594835 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.150 | 2017-07-26 12:03:36.660 | 0 | 0 | 0
| BK_PERSON_OF_OTHER_COMPANY | 1025594892 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.813 | 2017-07-26 12:03:37.047 | 0 | 0 | 0
| BK_BU_INFORMATION | 1041594949 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.027 | 2017-07-26 12:03:37.153 | 0 | 0 | 0
| BK_SHITSU_INFORMATION | 1073595063 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.297 | 2017-07-26 12:03:37.157 | 0 | 0 | 0
| BK_KAKARI_INFORMATION | 1105595177 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.550 | 2017-07-26 12:03:37.160 | 0 | 0 | 0
| BK_STAFF_DIVISION | 1137595291 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.507 | 2017-07-26 12:03:37.160 | 0 | 0 | 0
| BK_ABOUT_WORK | 1169595405 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.797 | 2017-07-26 12:03:37.163 | 0 | 0 | 0
| BK_JOB_CATEGORY | 1201595519 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.827 | 2017-07-26 12:03:37.163 | 0 | 0 | 0
| BK_QUALIFICATION | 1233595633 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:16.147 | 2017-07-26 12:03:37.160 | 0 | 0 | 0
| PERSON_OF_COMPANY | 1249595690 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.080 | 2017-07-26 12:03:37.433 | 0 | 0 | 0
| PERSON_OF_OTHER_COMPANY | 1265595747 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.113 | 2017-07-26 12:03:37.560 | 0 | 0 | 0
| BU_INFORMATION | 1281595804 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.130 | 2017-07-26 12:03:37.570 | 0 | 0 | 0
| SHITSU_INFORMATION | 1313595918 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.217 | 2017-07-26 12:03:37.570 | 0 | 0 | 0
| KAKARI_INFORMATION | 1345596032 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.257 | 2017-07-26 12:03:37.573 | 0 | 0 | 0
| STAFF_DIVISION | 1377596146 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.270 | 2017-07-26 12:03:37.577 | 0 | 0 | 0
| ABOUT_WORK | 1409596260 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.287 | 2017-07-26 12:03:37.577 | 0 | 0 | 0
| JOB_CATEGORY | 1441596374 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.300 | 2017-07-26 12:03:37.580 | 0 | 0 | 0
| QUALIFICATION | 1473596488 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:03:31.313 | 2017-07-26 12:03:37.573 | 0 | 0 | 0
主キー一覧 - 取得SQL：
SELECT
i.name AS index_name
,o.name AS table_name
,col.name AS column_name
FROM
sysindexkeys ik
,sysobjects o
,syscolumns col
,sysindexes i
WHERE
ik.id = o.id
AND ik.id = col.id
AND ik.colid = col.colid
AND ik.id = i.id
AND ik.indid = i.indid
AND o.xtype = 'U'
ORDER BY
i.name
,ik.id
,ik.indid
,ik.keyno
| index_name | table_name | column_name
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | STAFF_CODE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_BK_PERSON_OF_OTHER_COMPANY | BK_PERSON_OF_OTHER_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_PERSON_OF_OTHER_COMPANY | PERSON_OF_OTHER_COMPANY | STAFF_CODE
| PK__BK_ABOUT_WORK | BK_ABOUT_WORK | ABOUT_WORK_CODE
| PK__BK_BU_INFORMATION | BK_BU_INFORMATION | BU_CODE
| PK__BK_JOB_CATEGORY | BK_JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__BK_KAKARI_INFORMATION | BK_KAKARI_INFORMATION | KAKARI_CODE
| PK__BK_SHITSU_INFORMATION | BK_SHITSU_INFORMATION | SHITSU_CODE
| PK__BK_STAFF_DIVISION | BK_STAFF_DIVISION | STAFF_DIVISION_CODE
| PK__ABOUT_WORK | ABOUT_WORK | ABOUT_WORK_CODE
| PK__BU_INFORMATION | BU_INFORMATION | BU_CODE
| PK__JOB_CATEGORY | JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__KAKARI_INFORMATION | KAKARI_INFORMATION | KAKARI_CODE
| PK__SHITSU_INFORMATION | SHITSU_INFORMATION | SHITSU_CODE
| PK__STAFF_DIVISION | STAFF_DIVISION | STAFF_DIVISION_CODE
②復旧コマンド実行後 | コマンド：D:\ImportCSV\CSV取込>exec_ddl recovery_goguchi.sql
テーブル一覧 - 取得SQL：select * from sys.objects where type = 'U';
| name | object_id | principal_id | schema_id | parent_object_id | type | type_desc | create_date | modify_date | is_ms_shipped | is_published | is_schema_published
| PERSON_OF_COMPANY | 1009594835 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.150 | 2017-07-26 12:17:55.510 | 0 | 0 | 0
| PERSON_OF_OTHER_COMPANY | 1025594892 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.813 | 2017-07-26 12:17:55.587 | 0 | 0 | 0
| BU_INFORMATION | 1041594949 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.027 | 2017-07-26 12:17:55.597 | 0 | 0 | 0
| SHITSU_INFORMATION | 1073595063 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.297 | 2017-07-26 12:17:55.600 | 0 | 0 | 0
| KAKARI_INFORMATION | 1105595177 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.550 | 2017-07-26 12:17:55.600 | 0 | 0 | 0
| STAFF_DIVISION | 1137595291 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.507 | 2017-07-26 12:17:55.603 | 0 | 0 | 0
| ABOUT_WORK | 1169595405 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.797 | 2017-07-26 12:17:55.603 | 0 | 0 | 0
| JOB_CATEGORY | 1201595519 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.827 | 2017-07-26 12:17:55.607 | 0 | 0 | 0
| QUALIFICATION | 1233595633 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:16.147 | 2017-07-26 12:17:55.600 | 0 | 0 | 0
主キー一覧 - 取得SQL：
SELECT
i.name AS index_name
,o.name AS table_name
,col.name AS column_name
FROM
sysindexkeys ik
,sysobjects o
,syscolumns col
,sysindexes i
WHERE
ik.id = o.id
AND ik.id = col.id
AND ik.colid = col.colid
AND ik.id = i.id
AND ik.indid = i.indid
AND o.xtype = 'U'
ORDER BY
i.name
,ik.id
,ik.indid
,ik.keyno
| index_name | table_name | column_name
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_PERSON_OF_OTHER_COMPANY | PERSON_OF_OTHER_COMPANY | STAFF_CODE
| PK__ABOUT_WORK | ABOUT_WORK | ABOUT_WORK_CODE
| PK__BU_INFORMATION | BU_INFORMATION | BU_CODE
| PK__JOB_CATEGORY | JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__KAKARI_INFORMATION | KAKARI_INFORMATION | KAKARI_CODE
| PK__SHITSU_INFORMATION | SHITSU_INFORMATION | SHITSU_CODE
| PK__STAFF_DIVISION | STAFF_DIVISION | STAFF_DIVISION_CODE
③通常処理実行後
テーブル一覧 - 取得SQL：select * from sys.objects where type = 'U';
| name | object_id | principal_id | schema_id | parent_object_id | type | type_desc | create_date | modify_date | is_ms_shipped | is_published | is_schema_published
| BK_PERSON_OF_COMPANY | 1009594835 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.150 | 2017-07-26 12:20:14.660 | 0 | 0 | 0
| BK_PERSON_OF_OTHER_COMPANY | 1025594892 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.813 | 2017-07-26 12:20:14.730 | 0 | 0 | 0
| BK_BU_INFORMATION | 1041594949 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.027 | 2017-07-26 12:20:14.770 | 0 | 0 | 0
| BK_SHITSU_INFORMATION | 1073595063 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.297 | 2017-07-26 12:20:14.777 | 0 | 0 | 0
| BK_KAKARI_INFORMATION | 1105595177 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.550 | 2017-07-26 12:20:14.780 | 0 | 0 | 0
| BK_STAFF_DIVISION | 1137595291 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.507 | 2017-07-26 12:20:14.780 | 0 | 0 | 0
| BK_ABOUT_WORK | 1169595405 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.797 | 2017-07-26 12:20:14.783 | 0 | 0 | 0
| BK_JOB_CATEGORY | 1201595519 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.827 | 2017-07-26 12:20:14.783 | 0 | 0 | 0
| BK_QUALIFICATION | 1233595633 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:16.147 | 2017-07-26 12:20:14.780 | 0 | 0 | 0
| PERSON_OF_COMPANY | 1489596545 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.397 | 2017-07-26 12:20:14.967 | 0 | 0 | 0
| PERSON_OF_OTHER_COMPANY | 1505596602 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.433 | 2017-07-26 12:20:15.060 | 0 | 0 | 0
| BU_INFORMATION | 1521596659 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.450 | 2017-07-26 12:20:15.070 | 0 | 0 | 0
| SHITSU_INFORMATION | 1553596773 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.480 | 2017-07-26 12:20:15.070 | 0 | 0 | 0
| KAKARI_INFORMATION | 1585596887 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.490 | 2017-07-26 12:20:15.073 | 0 | 0 | 0
| STAFF_DIVISION | 1617597001 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.500 | 2017-07-26 12:20:15.077 | 0 | 0 | 0
| ABOUT_WORK | 1649597115 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.503 | 2017-07-26 12:20:15.077 | 0 | 0 | 0
| JOB_CATEGORY | 1681597229 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.510 | 2017-07-26 12:20:15.080 | 0 | 0 | 0
| QUALIFICATION | 1713597343 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.513 | 2017-07-26 12:20:15.073 | 0 | 0 | 0
主キー一覧 - 取得SQL：
SELECT
i.name AS index_name
,o.name AS table_name
,col.name AS column_name
FROM
sysindexkeys ik
,sysobjects o
,syscolumns col
,sysindexes i
WHERE
ik.id = o.id
AND ik.id = col.id
AND ik.colid = col.colid
AND ik.id = i.id
AND ik.indid = i.indid
AND o.xtype = 'U'
ORDER BY
i.name
,ik.id
,ik.indid
,ik.keyno
| index_name | table_name | column_name
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | STAFF_CODE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_BK_PERSON_OF_OTHER_COMPANY | BK_PERSON_OF_OTHER_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_PERSON_OF_OTHER_COMPANY | PERSON_OF_OTHER_COMPANY | STAFF_CODE
| PK__ABOUT_WORK | ABOUT_WORK | ABOUT_WORK_CODE
| PK__BK_ABOUT_WORK | BK_ABOUT_WORK | ABOUT_WORK_CODE
| PK__BK_BU_INFORMATION | BK_BU_INFORMATION | BU_CODE
| PK__BK_JOB_CATEGORY | BK_JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__BK_KAKARI_INFORMATION | BK_KAKARI_INFORMATION | KAKARI_CODE
| PK__BK_SHITSU_INFORMATION | BK_SHITSU_INFORMATION | SHITSU_CODE
| PK__BK_STAFF_DIVISION | BK_STAFF_DIVISION | STAFF_DIVISION_CODE
| PK__BU_INFORMATION | BU_INFORMATION | BU_CODE
| PK__JOB_CATEGORY | JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__KAKARI_INFORMATION | KAKARI_INFORMATION | KAKARI_CODE
| PK__SHITSU_INFORMATION | SHITSU_INFORMATION | SHITSU_CODE
| PK__STAFF_DIVISION | STAFF_DIVISION | STAFF_DIVISION_CODE
No.21
①復旧コマンド実行前
テーブル一覧 - 取得SQL：select * from sys.objects where type = 'U';
| name | object_id | principal_id | schema_id | parent_object_id | type | type_desc | create_date | modify_date | is_ms_shipped | is_published | is_schema_published
| BK_PERSON_OF_COMPANY | 1009594835 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.150 | 2017-07-26 12:20:14.660 | 0 | 0 | 0
| BK_PERSON_OF_OTHER_COMPANY | 1025594892 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.813 | 2017-07-26 12:20:14.730 | 0 | 0 | 0
| BK_BU_INFORMATION | 1041594949 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.027 | 2017-07-26 12:20:14.770 | 0 | 0 | 0
| BK_SHITSU_INFORMATION | 1073595063 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.297 | 2017-07-26 12:20:14.777 | 0 | 0 | 0
| BK_KAKARI_INFORMATION | 1105595177 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.550 | 2017-07-26 12:20:14.780 | 0 | 0 | 0
| BK_STAFF_DIVISION | 1137595291 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.507 | 2017-07-26 12:20:14.780 | 0 | 0 | 0
| BK_ABOUT_WORK | 1169595405 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.797 | 2017-07-26 12:20:14.783 | 0 | 0 | 0
| BK_JOB_CATEGORY | 1201595519 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.827 | 2017-07-26 12:20:14.783 | 0 | 0 | 0
| BK_QUALIFICATION | 1233595633 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:16.147 | 2017-07-26 12:20:14.780 | 0 | 0 | 0
| PERSON_OF_OTHER_COMPANY | 1505596602 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.433 | 2017-07-26 12:20:15.060 | 0 | 0 | 0
| BU_INFORMATION | 1521596659 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.450 | 2017-07-26 12:20:15.070 | 0 | 0 | 0
| SHITSU_INFORMATION | 1553596773 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.480 | 2017-07-26 12:20:15.070 | 0 | 0 | 0
| STAFF_DIVISION | 1617597001 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.500 | 2017-07-26 12:20:15.077 | 0 | 0 | 0
| ABOUT_WORK | 1649597115 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.503 | 2017-07-26 12:20:15.077 | 0 | 0 | 0
| JOB_CATEGORY | 1681597229 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.510 | 2017-07-26 12:20:15.080 | 0 | 0 | 0
| QUALIFICATION | 1713597343 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:20:08.513 | 2017-07-26 12:20:15.073 | 0 | 0 | 0
主キー一覧 - 取得SQL：
SELECT
i.name AS index_name
,o.name AS table_name
,col.name AS column_name
FROM
sysindexkeys ik
,sysobjects o
,syscolumns col
,sysindexes i
WHERE
ik.id = o.id
AND ik.id = col.id
AND ik.colid = col.colid
AND ik.id = i.id
AND ik.indid = i.indid
AND o.xtype = 'U'
ORDER BY
i.name
,ik.id
,ik.indid
,ik.keyno
| index_name | table_name | column_name
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | STAFF_CODE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_BK_PERSON_OF_OTHER_COMPANY | BK_PERSON_OF_OTHER_COMPANY | STAFF_CODE
| IDX_PERSON_OF_OTHER_COMPANY | PERSON_OF_OTHER_COMPANY | STAFF_CODE
| PK__ABOUT_WORK | ABOUT_WORK | ABOUT_WORK_CODE
| PK__BK_ABOUT_WORK | BK_ABOUT_WORK | ABOUT_WORK_CODE
| PK__BK_BU_INFORMATION | BK_BU_INFORMATION | BU_CODE
| PK__BK_JOB_CATEGORY | BK_JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__BK_KAKARI_INFORMATION | BK_KAKARI_INFORMATION | KAKARI_CODE
| PK__BK_SHITSU_INFORMATION | BK_SHITSU_INFORMATION | SHITSU_CODE
| PK__BK_STAFF_DIVISION | BK_STAFF_DIVISION | STAFF_DIVISION_CODE
| PK__BU_INFORMATION | BU_INFORMATION | BU_CODE
| PK__JOB_CATEGORY | JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__SHITSU_INFORMATION | SHITSU_INFORMATION | SHITSU_CODE
| PK__STAFF_DIVISION | STAFF_DIVISION | STAFF_DIVISION_CODE
②復旧コマンド実行後 | コマンド：D:\ImportCSV\CSV取込>exec_ddl recovery_goguchi.sql
テーブル一覧 - 取得SQL：select * from sys.objects where type = 'U';
| name | object_id | principal_id | schema_id | parent_object_id | type | type_desc | create_date | modify_date | is_ms_shipped | is_published | is_schema_published
| PERSON_OF_COMPANY | 1009594835 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.150 | 2017-07-26 13:12:30.793 | 0 | 0 | 0
| PERSON_OF_OTHER_COMPANY | 1025594892 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.813 | 2017-07-26 13:12:30.870 | 0 | 0 | 0
| BU_INFORMATION | 1041594949 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.027 | 2017-07-26 13:12:30.880 | 0 | 0 | 0
| SHITSU_INFORMATION | 1073595063 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.297 | 2017-07-26 13:12:30.883 | 0 | 0 | 0
| KAKARI_INFORMATION | 1105595177 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.550 | 2017-07-26 13:12:30.883 | 0 | 0 | 0
| STAFF_DIVISION | 1137595291 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.507 | 2017-07-26 13:12:30.887 | 0 | 0 | 0
| ABOUT_WORK | 1169595405 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.797 | 2017-07-26 13:12:30.890 | 0 | 0 | 0
| JOB_CATEGORY | 1201595519 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.827 | 2017-07-26 13:12:30.890 | 0 | 0 | 0
| QUALIFICATION | 1233595633 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:16.147 | 2017-07-26 13:12:30.887 | 0 | 0 | 0
主キー一覧 - 取得SQL：
SELECT
i.name AS index_name
,o.name AS table_name
,col.name AS column_name
FROM
sysindexkeys ik
,sysobjects o
,syscolumns col
,sysindexes i
WHERE
ik.id = o.id
AND ik.id = col.id
AND ik.colid = col.colid
AND ik.id = i.id
AND ik.indid = i.indid
AND o.xtype = 'U'
ORDER BY
i.name
,ik.id
,ik.indid
,ik.keyno
| index_name | table_name | column_name
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_PERSON_OF_OTHER_COMPANY | PERSON_OF_OTHER_COMPANY | STAFF_CODE
| PK__ABOUT_WORK | ABOUT_WORK | ABOUT_WORK_CODE
| PK__BU_INFORMATION | BU_INFORMATION | BU_CODE
| PK__JOB_CATEGORY | JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__KAKARI_INFORMATION | KAKARI_INFORMATION | KAKARI_CODE
| PK__SHITSU_INFORMATION | SHITSU_INFORMATION | SHITSU_CODE
| PK__STAFF_DIVISION | STAFF_DIVISION | STAFF_DIVISION_CODE
③通常処理実行後
テーブル一覧 - 取得SQL：select * from sys.objects where type = 'U';
| name | object_id | principal_id | schema_id | parent_object_id | type | type_desc | create_date | modify_date | is_ms_shipped | is_published | is_schema_published
| BK_PERSON_OF_COMPANY | 1009594835 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.150 | 2017-07-26 13:18:22.550 | 0 | 0 | 0
| BK_PERSON_OF_OTHER_COMPANY | 1025594892 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:13.813 | 2017-07-26 13:18:22.620 | 0 | 0 | 0
| BK_BU_INFORMATION | 1041594949 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.027 | 2017-07-26 13:18:22.630 | 0 | 0 | 0
| BK_SHITSU_INFORMATION | 1073595063 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.297 | 2017-07-26 13:18:22.633 | 0 | 0 | 0
| BK_KAKARI_INFORMATION | 1105595177 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:14.550 | 2017-07-26 13:18:22.637 | 0 | 0 | 0
| BK_STAFF_DIVISION | 1137595291 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.507 | 2017-07-26 13:18:22.637 | 0 | 0 | 0
| BK_ABOUT_WORK | 1169595405 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.797 | 2017-07-26 13:18:22.640 | 0 | 0 | 0
| BK_JOB_CATEGORY | 1201595519 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:15.827 | 2017-07-26 13:18:22.640 | 0 | 0 | 0
| BK_QUALIFICATION | 1233595633 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 12:00:16.147 | 2017-07-26 13:18:22.637 | 0 | 0 | 0
| PERSON_OF_COMPANY | 1729597400 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.450 | 2017-07-26 13:18:22.857 | 0 | 0 | 0
| PERSON_OF_OTHER_COMPANY | 1745597457 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.480 | 2017-07-26 13:18:22.927 | 0 | 0 | 0
| BU_INFORMATION | 1761597514 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.523 | 2017-07-26 13:18:22.937 | 0 | 0 | 0
| SHITSU_INFORMATION | 1793597628 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.540 | 2017-07-26 13:18:22.940 | 0 | 0 | 0
| KAKARI_INFORMATION | 1825597742 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.553 | 2017-07-26 13:18:22.940 | 0 | 0 | 0
| STAFF_DIVISION | 1857597856 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.563 | 2017-07-26 13:18:22.943 | 0 | 0 | 0
| ABOUT_WORK | 1889597970 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.583 | 2017-07-26 13:18:22.947 | 0 | 0 | 0
| JOB_CATEGORY | 1921598084 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.597 | 2017-07-26 13:18:22.947 | 0 | 0 | 0
| QUALIFICATION | 1953598198 | NULL | 1 | 0 | U | USER_TABLE | 2017-07-26 13:18:15.620 | 2017-07-26 13:18:22.943 | 0 | 0 | 0
主キー一覧 - 取得SQL：
SELECT
i.name AS index_name
,o.name AS table_name
,col.name AS column_name
FROM
sysindexkeys ik
,sysobjects o
,syscolumns col
,sysindexes i
WHERE
ik.id = o.id
AND ik.id = col.id
AND ik.colid = col.colid
AND ik.id = i.id
AND ik.indid = i.indid
AND o.xtype = 'U'
ORDER BY
i.name
,ik.id
,ik.indid
,ik.keyno
| index_name | table_name | column_name
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | STAFF_CODE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_BK_PERSON_OF_COMPANY | BK_PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_BK_PERSON_OF_OTHER_COMPANY | BK_PERSON_OF_OTHER_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | STAFF_CODE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_START_DATE
| IDX_PERSON_OF_COMPANY | PERSON_OF_COMPANY | ORIGINAL_BELONGING_CODE
| IDX_PERSON_OF_OTHER_COMPANY | PERSON_OF_OTHER_COMPANY | STAFF_CODE
| PK__BK_ABOUT_WORK | BK_ABOUT_WORK | ABOUT_WORK_CODE
| PK__BK_BU_INFORMATION | BK_BU_INFORMATION | BU_CODE
| PK__BK_JOB_CATEGORY | BK_JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__BK_KAKARI_INFORMATION | BK_KAKARI_INFORMATION | KAKARI_CODE
| PK__BK_SHITSU_INFORMATION | BK_SHITSU_INFORMATION | SHITSU_CODE
| PK__BK_STAFF_DIVISION | BK_STAFF_DIVISION | STAFF_DIVISION_CODE
| PK__ABOUT_WORK | ABOUT_WORK | ABOUT_WORK_CODE
| PK__BU_INFORMATION | BU_INFORMATION | BU_CODE
| PK__JOB_CATEGORY | JOB_CATEGORY | JOB_CATEGORY_CODE
| PK__KAKARI_INFORMATION | KAKARI_INFORMATION | KAKARI_CODE
| PK__SHITSU_INFORMATION | SHITSU_INFORMATION | SHITSU_CODE
| PK__STAFF_DIVISION | STAFF_DIVISION | STAFF_DIVISION_CODE
予備（バックアップ）テーブル
9テーブル
運用（号口）テーブル
9テーブル
予備（バックアップ）テーブル用インデックス
運用（号口）テーブル用主キー
運用（号口）テーブル
9テーブルのみ残っている
運用（号口）テーブル用主キーのみ残っている
予備（バックアップ）テーブル
9テーブル
運用（号口）テーブル
9テーブル
予備（バックアップ）テーブル用主キー
運用（号口）テーブル用主キー
復旧コマンド実行前と同じ状態に戻った
予備（バックアップ）テーブル用主キー
運用（号口）テーブル用インデックス
運用（号口）テーブル用インデックスのみ残っている
予備（バックアップ）テーブル用インデックス
運用（号口）テーブル用インデックス
予備（バックアップ）テーブル
9テーブル
運用（号口）テーブル
7テーブル
予備（バックアップ）テーブル用インデックス
運用（号口）テーブル用主キー
運用（号口）テーブル
9テーブル全てが復旧されている
運用（号口）テーブル用主キーのみ残っている
予備（バックアップ）テーブル
9テーブル
運用（号口）テーブル
9テーブル
予備（バックアップ）テーブル用主キー
運用（号口）テーブル用主キー
予備（バックアップ）テーブル用主キー
運用（号口）テーブル用インデックス
運用（号口）テーブル用インデックス
予備（バックアップ）テーブル用インデックス
運用（号口）テーブル用インデックス
PERSON_OF_COMPANYとKAKARI_INFORMATIONがない状態
PERSON_OF_COMPANYのインデックスがない状態
KAKARI_INFORMATIONの主キーがない状態
PERSON_OF_COMPANYのインデックスも戻っている
KAKARI_INFORMATIONの主キーも戻っている
PERSON_OF_COMPANYとKAKARI_INFORMATIONも戻っている
運用テーブルの数と主キーとインデックスの数が正常に戻った